## Sheet1
Test Cases and Execution status tracking
Task :Creation of Test Cases
Project | Real Estate
Sl no. | Module | # of Test Cases written and Reviewed | Date | Estimated effort | Actual Effort | Reason for variannce if any
1 | All Properties | 2 | 6.09.2021 | 2hrs | 2 hrs | N/A
2 | Add new property | 1 | 6.09.2021 | 1hr | 1hr | N/A
3 | Add new features | 3 | 6.09.2021 | 1hr | 1.5hrs | Requirement clarity was not mentionned
4 | Add new regions | 3 | 6.09.2021 | 1hr | 1.5hrs | Requirement clarity was not mentionned
5 | Properties settings | 1 | 6.09.2021 | 1hr | 1hr | N/A
| Total # of test cases | 10

## Sheet2
Task: Execution of Test Cases
Sl no | Module | #of Test Cases | Date | H | M | L | # of Defects
1 | All Properties | 2 | 6.09.2021 | 0 | 0 | 2 | 1
2 | Add new property | 1 | 6.09.2021 | 1 | 0 | 0 | 0
3 | Add new features | 3 | 6.09.2021 | 1 | 0 | 2 | 0
4 | Add new regions | 3 | 6.09.2021 | 1 | 0 | 2 | 0
5 | Properties settings | 1 | 6.09.2021 | 0 | 0 | 1 | 1